| 1 Project Management and Planning |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS code | Work item | Expected deliverable | Proposed owner | Proposed reviewer |
| 1.1 | Complete the PA1 report | The team's project proposal and plan. | Trang (coord.) | — |
| 1.1.1 | Write the PA1 Vision | Sections 2.1–2.4: problem statement, product positioning, stakeholders, MoSCoW features and exclusions. | Phuc | Trang |
| 1.1.2 | Consolidate the project-wide WBS | The framework and members' decompositions, consistent codes, resolved gaps and duplicates, and review records. | Phuc | Minh |
| 1.1.3 | Provide estimates and review the plan | Effort estimates and assumptions for Phuc's work; feedback on sections 4.1 and 4.4–4.6 and the contribution table compiled by Trang. | Phuc | Trang |
| 1.1.4 | Review and hand over Phuc's PA1 contribution | Content revised following feedback; task, commit and PR links; individual AI Usage Log. | Phuc | Trang |
| 1.1.5 | Define the process and phase gates | Section 4.1: Waterfall model and rationale, exit criteria for each PA, baselining procedure and change requests. | Trang | Phuc |
| 1.1.6 | Develop the schedule and identify the critical path | PA1 section 4.4: schedule using this WBS's codes, durations, dependencies and PA milestones; Gantt chart for weeks 1–11, critical path and slack. Use branch 5.3 for room booking and 5.4 for history and administration, with the corresponding level-3 codes for individual packages. | Trang | Phuc |
| 1.1.7 | Assign roles and responsibilities | Section 4.5: primary and backup roles for four members, cross-review matrix and prohibition on self-approval. | Trang | Phuc |
| 1.1.8 | Estimate staffing and costs | Section 4.6: capacity in hours per week, effort from section 4.3, hourly rates, infrastructure costs, contingency and total budget. Capacity assumption: 8–10 hours per member per week. | Trang | Phuc |
| 1.1.9 | Compile member contributions | Section 1: contribution percentages totaling 100%, supported by actual task, commit or PR links. | Trang | Phuc |
| 1.1.10 | Assemble, review and submit PA1 | Complete PA1 report, section 7 AI Usage Log, contribution table and rubric checklist; PDF and source files in the appropriate repository location, Moodle submission and baseline-pa1 tag. | Trang | Phuc |
| 1.1.11 | Consolidate work estimates | Three-point O/M/P estimates and expected effort for leaf-level work packages, with assumptions and member input; provide PA1 section 4.3 and inputs for Trang's schedule, staffing and cost plan. Sum effort only at the leaf level; estimate recurring work by occurrence to avoid double counting. | Nhat Anh | Trang |
| 1.1.12 | Prepare the risk management plan | PA1 section 5 risk register with at least five risks: category, Probability, Loss and RE = Probability × Loss using the course scale; triggers, mitigation, contingency and risk owner. | Nhat Anh | Minh |
| 1.1.13 | Review and hand over Nhat Anh's PA1 contribution | WBS, estimates and risks revised following feedback; task and PR links and individual AI Usage Log sent to Trang for consolidation; unresolved items clearly identified for team confirmation. | Nhat Anh | Trang |
| 1.1.14 | Write the PA1 Proposed Solution | PA1 section 3: C4 System Context, technology stack and rationale, hardware and operating environment; diagrams stored in the existing team repository structure. | Minh | Nhat Anh |
| 1.1.15 | Write the technology selection ADR | ADR-001: React + Vite, NestJS on Node.js, PostgreSQL on Supabase, Prisma, Vercel, Cloudflare and GitHub Actions; alternatives and consequences. The architecture ADR at 3.1.3 references this decision without duplicating it. | Minh | Nhat Anh |
| 1.1.16 | Provide estimates and hand over Minh's PA1 contribution | Effort and assumptions for branches 1.2, 5 and 6.2 sent to Nhat Anh; content revised after review, PR links and individual AI Usage Log. | Minh | Nhat Anh |
| 1.2 | Set up tools and collaboration | Repository, task board, PR workflow, communication channels and setup evidence; separate from application deployment. | Trang (coord.) | — |
| 1.2.1 | Create the repository and directory structure | GitHub repository following the team's structure and PA1 section 6; README, .gitignore and .env.example. Prepare the repository for Trang to grant and verify access under 1.2.5. | Minh | Nhat Anh |
| 1.2.2 | Set up the PR workflow and main protection | PR template, branch and commit conventions, main protection rules for the repository owner to apply, and evidence screenshots. | Minh | Nhat Anh |
| 1.2.3 | Set up the task board | GitHub Projects with status columns, WBS code, assignee, reviewer and due date fields; enter the agreed WBS work packages. | Trang | Phuc |
| 1.2.4 | Set up communication channels | Discord general and workstream channels with the TA included; communication rules and response times. | Trang | Phuc |
| 1.2.5 | Grant instructor and TA access | Trang grants and verifies instructor/TA access to the repository, GitHub Projects and Discord; screenshots for PA1 section 6. Exclude repository preparation already covered by 1.2.1. | Trang | Phuc |
| 1.2.6 | Set up meetings and report templates | Recurring meeting schedule, minutes template and docs/management/weekly/W<week>-status.md template. | Trang | Phuc |
| 1.3 | Monitor and manage the project | Weekly reports, progress and risk tracking, baselines, contributions, AI logs, and coordination of PA reviews and submissions. | Trang | — |
| 1.3.1 | Write weekly status reports | Reports for weeks 2–10: completed work, delayed work, issues, risks and next week's plan. | Trang | Phuc |
| 1.3.2 | Hold meetings and record minutes | Minutes for each meeting: decisions, action items, owners and deadlines; absences recorded according to the team contract. | Trang | Phuc |
| 1.3.3 | Track progress and risks | Updated task board, comparison with the baseline schedule, risk register maintained with Nhat Anh, and recovery actions for delays. | Trang | Phuc |
| 1.3.4 | Manage baselines and changes | baseline-paX tags and snapshots in /pa/PAx; change request log with impact analysis; baseline change appendix in the next PA. | Trang | Phuc |
| 1.3.5 | Track contributions and AI usage | Contribution table for each PA based on tasks, commits and PRs; reminders to update docs/ai-usage/<Name>/; logs consolidated into each PA. | Trang | Phuc |
| 1.3.6 | Coordinate PA2–PA4 reviews and submissions | Cross-review schedule, rubric checklists, PDF and source files submitted to Moodle on time, and baseline tag confirmation. | Trang | Phuc |

| 2 Requirements Analysis |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS code | Work item | Expected deliverable | Proposed owner | Proposed reviewer |
| 2.1 | Elicit needs and define scope | Inputs and scope agreed by the team. | Phuc | — |
| 2.1.1 | Analyze the simulated context and needs | Description of the simulated unit, assumed processes, needs of the three roles and unverified assumptions; questions for team review. Record field-survey findings only when supported by evidence. | Phuc | Nhat Anh |
| 2.1.2 | Confirm scope with the team | Agreement on F01–F09 Must-have features, exclusions and changes from PA0/PA1. F10–F11 remain Could-have in the Vision and are not decomposed or estimated for implementation in the current WBS. | Phuc | Nhat Anh |
| 2.2 | Specify requirements and business rules | Requirements with identifiers, priorities and acceptance criteria. | Phuc | — |
| 2.2.1 | Specify accounts and permissions | F01/F09: Borrower, Resource Manager and Admin; assigned-resource scope; account creation/locking and acting on behalf of other roles. Only Resource Managers may change pickup appointments. | Phuc | Minh |
| 2.2.2 | Specify the catalog and availability | F02: equipment and room information, capacity, search and unavailable status. | Phuc | Minh |
| 2.2.3 | Specify loan requests and approvals | F03: one equipment item per request, purpose, return deadline, availability checks and reservation on approval; confirmed pickup appointment. Borrowers request changes outside the system; only Resource Managers change the appointment. Exclude the F11 in-app change-request workflow. | Phuc | Minh |
| 2.2.4 | Specify handover, return and overdue handling | F04: actual handover and return timestamps, return deadline, overdue conditions and availability updates. | Phuc | Minh |
| 2.2.5 | Specify cancellation and missed pickups | Borrowers may cancel pending or approved requests before handover; after collection, the equipment must be returned. Automatically cancel uncollected requests after 24 hours from the currently valid confirmed pickup appointment and release the reservation. | Phuc | Minh |
| 2.2.6 | Specify the calendar and room booking requests | F05/F06: one room on one day, time interval and attendee count; information displayed on the calendar. | Phuc | Minh |
| 2.2.7 | Specify room booking approval and cancellation | F07: prevent overlaps on approval; allow cancellation before the start time. Rooms under maintenance are unavailable: disable booking in the UI and reject booking requests in the backend. Handling existing approved bookings affected by maintenance remains outside the system. | Phuc | Minh |
| 2.2.8 | Specify history and state corrections | F08/F09: resource states and events, viewing permissions and responsible actors; Admin corrections with reasons. | Phuc | Minh |
| 2.2.9 | Write non-functional requirements | Measurable performance, security, availability and usability requirements, with measurement conditions. | Phuc | Minh |
| 2.3 | Develop use cases and UI prototypes | Interaction models, workflows and illustrative screens. | Phuc | — |
| 2.3.1 | Create the use case model | Actors, use cases and include/extend relationships where appropriate; mapping to F01–F09. | Phuc | Nhat Anh |
| 2.3.2 | Write account and administration use cases | Login, account creation/locking, role assignment and resource allocation; preconditions, postconditions and error flows. | Phuc | Nhat Anh |
| 2.3.3 | Write catalog use cases | View/search, update resources and availability; verify permission scope. | Phuc | Nhat Anh |
| 2.3.4 | Write loan request and approval use cases | Submit, approve/reject and confirm pickup; Resource Manager changes the appointment after contact outside the system; handle equipment reserved by another request. Exclude F11 from required flows. | Phuc | Nhat Anh |
| 2.3.5 | Write handover, return and cancellation use cases | Handover, return and overdue handling; Borrower cancellation while pending or approved but not handed over; return required after collection. Missed-pickup expiry and flows around the 24-hour boundary. | Phuc | Nhat Anh |
| 2.3.6 | Write room booking use cases | View calendar, submit, approve/reject and cancel; overlapping times and excess capacity; block booking of maintenance/unavailable rooms in both the UI and backend. | Phuc | Nhat Anh |
| 2.3.7 | Write history and correction use cases | Role-based history access; Admin corrections of erroneous states with reasons and handling of related requests. | Phuc | Nhat Anh |
| 2.3.8 | Create mockups for core flows | Representative screens for all three roles, aligned with use cases; detailed UI design is deferred to PA3. | Phuc | Nhat Anh |
| 2.3.9 | Establish traceability and hand over the SRS | Requirements–use cases–mockups matrix, review minutes, resolved feedback, and source/PDF files for PA2 submission. | Phuc | Nhat Anh |

| 3 System Design |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS code | Work item | Expected deliverable | Proposed owner | Proposed reviewer |
| 3.1 | Design the architecture | Components, deployment environments and architectural decisions. | Phuc | — |
| 3.1.1 | Create C4 Context and Container diagrams | System boundary, three user roles, frontend, backend and database; rationale for the decomposition. | Phuc | Minh |
| 3.1.2 | Create component and deployment diagrams | React + Vite, NestJS, Prisma, PostgreSQL/Supabase, Vercel and Cloudflare components and deployment; responsibilities, runtime environments and pickup-expiry trigger mechanism from 3.1.5. | Phuc | Minh |
| 3.1.3 | Write the application structure ADR | Context, alternatives, application structure decision and consequences; reference ADR-001 at 1.1.15 for technology selection to avoid duplicate effort. | Phuc | Minh |
| 3.1.4 | Write the concurrency handling ADR | Decisions protecting equipment approval/reservation and preventing overlapping room bookings; trade-offs and constraints. | Phuc | Minh |
| 3.1.5 | Write the pickup-expiry ADR | Detect and handle the 24-hour deadline based on the currently valid pickup appointment; update the deadline when a Resource Manager changes the appointment; pre-handover checks and conflicting operations. | Phuc | Minh |
| 3.2 | Design data and objects | Data and class models and business interactions. | Phuc | — |
| 3.2.1 | Design the ERD | Accounts, resources, assignments, loan/booking requests and history; relationships and cardinalities. | Phuc | Minh |
| 3.2.2 | Specify tables and constraints | Keys, data types, normalization, indexes and constraints; preserve history when accounts or resources are deactivated. | Phuc | Minh |
| 3.2.3 | Design classes and responsibilities | Class diagram and specifications; explained design principles/patterns aligned with the architecture. | Phuc | Minh |
| 3.2.4 | Design component interfaces | Core API contracts: inputs, outputs, errors and permissions; mapping to use cases for frontend/backend coordination. | Phuc | Minh |
| 3.2.5 | Design equipment state diagrams | Distinguish equipment states from loan-request states; transitions on approval, handover, return, cancellation and expiry. | Phuc | Minh |
| 3.2.6 | Design room state diagrams | Distinguish room availability from booking status; maintenance/unavailable rooms reject new booking requests. | Phuc | Minh |
| 3.2.7 | Design equipment loan sequence diagrams | Submit/approve/reserve, handover/return and cancellation before handover; Resource Manager appointment changes; handover–expiry races; consistent validation and updates. | Phuc | Minh |
| 3.2.8 | Design room booking sequence diagrams | Schedule validation and approval, concurrent conflicts, cancellation and release of reserved intervals. | Phuc | Minh |
| 3.2.9 | Design Admin state corrections | Sequence for validation and correction of resources and related requests; record before/after values and reasons; prevent inconsistent states. | Phuc | Minh |
| 3.3 | Design and review the UI | Screen designs, traceability and handover package. | Phuc | — |
| 3.3.1 | Design screen flows | Borrower, Resource Manager and Admin navigation, screen connections and access permissions. | Phuc | Nhat Anh |
| 3.3.2 | Specify the Borrower UI | Catalog, loan requests, room calendar, booking and personal history; cancellation before handover; instructions to contact the Resource Manager outside the system to change pickup time; block maintenance-room bookings and display errors. No F11 screen. | Phuc | Nhat Anh |
| 3.3.3 | Specify Resource Manager and Admin UIs | Approval/handover/return, resources, accounts/assignments, history and state corrections; pickup-time changes are shown and permitted only for Resource Managers. | Phuc | Nhat Anh |
| 3.3.4 | Review accessibility | Checklist for keyboard navigation, labels, error messages and readability; record design changes. | Phuc | Nhat Anh |
| 3.3.5 | Check design against the SRS | Requirements–components–data–UI matrix; list changes requiring SRS updates. | Phuc | Nhat Anh |
| 3.3.6 | Review and hand over PA3 | Review minutes, resolved feedback, and design source/PDF files for Trang to coordinate submission. | Phuc | Nhat Anh |

| 4 Test Planning |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS code | Work item | Expected deliverable | Proposed owner | Proposed reviewer |
| 4.1 | Plan testing | Test scope, strategy, environment and criteria. | Nhat Anh | — |
| 4.1.1 | Define test scope and basis | F01–F09 Must-have features, non-functional requirements and business rules; references to the PA2 SRS, PA3 design and ADRs. F10–F11 are outside the current execution plan. | Nhat Anh | Phuc |
| 4.1.2 | Develop the test strategy and priorities | Unit, integration, system/E2E and regression testing; prioritize core flows, permissions, equipment reservations, room overlaps and pickup expiry; identify manual and automated tests. Unit tests are developed under branch 5. | Nhat Anh | Phuc |
| 4.1.3 | Define test environments and data | React + Vite, NestJS and PostgreSQL environments matching the chosen stack; accounts for three roles, resources assigned to different Resource Managers, state data and reset procedure; separate test data without real personal information. | Nhat Anh | Phuc |
| 4.1.4 | Define entry and exit criteria | Test entry checklist, pass/fail criteria, exit criteria and proposed coverage thresholds for team confirmation; handling blocked tests and unresolved defects. High coverage alone does not establish acceptance. | Nhat Anh | Phuc |
| 4.1.5 | Define defect management and test assignments | Bug report template, severity/priority, defect lifecycle, fixer and retester; tasks and dependencies sent to Trang for scheduling; fixers must not verify closure of their own defects. | Nhat Anh | Phuc |
| 4.2 | Design test cases | Test cases for Must-have features, business rules, error flows and permissions. | Nhat Anh | — |
| 4.2.1 | Design account and permission tests | F01/F09: login/logout, invalid credentials, invalid sessions and locked accounts; all three roles; API and UI authorization, including access outside a Resource Manager's assigned scope. | Nhat Anh | Phuc |
| 4.2.2 | Design resource catalog tests | F02: view/search, authorized create/update, invalid data, capacity and availability; Resource Managers edit only assigned resources while Admin manages all resources. | Nhat Anh | Phuc |
| 4.2.3 | Design equipment request and approval tests | F03: one equipment item per request, purpose, return deadline, approval/rejection and pickup confirmation; prevent approval of already reserved equipment and concurrent approvals reserving the same item. | Nhat Anh | Phuc |
| 4.2.4 | Design handover, return and overdue tests | F04: handover/return preconditions, actual timestamps, before/after states and availability; before/at/after return-deadline cases per the SRS; reject duplicate operations and invalid transitions. | Nhat Anh | Phuc |
| 4.2.5 | Design cancellation, rescheduling and pickup-expiry tests | Borrowers cancel pending or approved requests before handover; return is required afterward. Only Resource Managers change appointments. Test just before/at/after the valid appointment + 24 hours per the SRS/ADR; rescheduling updates expiry; expiry releases reservations; handover–expiry races preserve consistency. | Nhat Anh | Phuc |
| 4.2.6 | Design calendar and room request tests | F05/F06: room/day calendar, time order, valid dates, attendee count and capacity; unavailable rooms have disabled booking controls and reject direct API requests. | Nhat Anh | Phuc |
| 4.2.7 | Design room approval and cancellation tests | F07: approval/rejection, partial/full overlaps, adjacent intervals per the SRS and concurrent approvals; cancellation before the start time, time boundaries and schedule release after cancellation. | Nhat Anh | Phuc |
| 4.2.8 | Design history and administration tests | F08/F09: history access by role/scope, account creation/locking, role and resource assignment; locking preserves history. Admin corrections record reasons, before/after values, actor and timestamp; resource and related-request states remain consistent. | Nhat Anh | Phuc |
| 4.2.9 | Design non-functional tests | Performance, security, availability and usability cases against measurable SRS criteria; load data, measurement conditions and expected results. Check keyboard navigation, labels, error messages and readability against the PA3 design. | Nhat Anh | Phuc |
| 4.3 | Establish traceability and review PA4 | Requirements–test cases matrix and reviewed test documentation. | Nhat Anh | — |
| 4.3.1 | Build the test traceability matrix | Requirements–use cases/business rules–test cases matrix covering F01–F09 and non-functional requirements; identify untested requirements and tests without a requirement basis. | Nhat Anh | Phuc |
| 4.3.2 | Review the plan and test cases | Cross-review minutes with Phuc/Minh: clarity, business correctness, test design techniques, data, executability and expected results; feedback and assigned action owners. | Nhat Anh | Phuc |
| 4.3.3 | Complete and hand over PA4 | Test plan, cases and traceability revised after review; package checklist, unresolved items, source/PDF files, PR links and individual AI Usage Log sent to Trang for submission coordination. | Nhat Anh | Phuc |

| 5 Software Implementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS code | Work item | Expected deliverable | Proposed owner | Proposed reviewer |
| 5.1 | Implement the foundation and access control | React/Node.js/PostgreSQL foundation, accounts and three roles. Each branch 5 package includes the relevant API, UI and unit tests, review by another member and passing CI. | Minh | — |
| 5.1.1 | Set up the application scaffold | NestJS API, React + Vite client, Prisma, oxlint/Prettier/Husky and environment configuration; working npm run dev and /api/health. | Minh | Nhat Anh |
| 5.1.2 | Create the database schema and migrations | Prisma schema based on the PA3 ERD, migrations and indexes; exclusion constraint preventing overlapping room bookings; migrations run successfully on Supabase. | Minh | Nhat Anh |
| 5.1.3 | Implement login and sessions | F01: login/logout, password hashing, JWT in an httpOnly cookie, locked-account blocking and login screen. | Minh | Nhat Anh |
| 5.1.4 | Implement role-based access control | F01: server guards checking roles and Resource Manager resource scope; role-based client navigation. | Minh | Nhat Anh |
| 5.2 | Implement the catalog and equipment loans | Catalog, approval/handover/return, cancellation, overdue handling, pickup rescheduling and expiry. | By level-3 package | — |
| 5.2.1 | Implement equipment and room catalogs | F02: create/update/view, search, capacity and unavailable status; Resource Managers edit assigned resources and Admin edits all resources. | Phuc | Minh |
| 5.2.2 | Implement loan requests and approvals | F03: one equipment item per request, purpose and return date; approval reserves equipment in a transaction with row locking; pickup appointment confirmation; concurrent approval tests. | Minh | Nhat Anh |
| 5.2.3 | Implement handover, return and overdue handling | F04: actual handover/return timestamps, availability updates and overdue list. | Nhat Anh | Minh |
| 5.2.4 | Implement cancellation, pickup rescheduling and expiry | Borrowers cancel pending or approved requests before handover; only Resource Managers change pickup appointments. Automatically cancel uncollected requests 24 hours after the valid appointment and release reservations according to WBS 3.1.5; test the 24-hour boundary. Borrowers request rescheduling outside the system; exclude F11. | Minh | Nhat Anh |
| 5.3 | Implement room booking | Calendar, submission/approval/cancellation, overlap prevention and blocking unavailable rooms. | Trang | — |
| 5.3.1 | Implement the room calendar | F05: approved bookings by room and day. | Trang | Phuc |
| 5.3.2 | Implement room booking requests | F06: validate time order, future dates and capacity; disable booking of unavailable rooms in the UI and reject it in the backend. | Trang | Phuc |
| 5.3.3 | Implement booking approval, conflict prevention and cancellation | F07: database constraints block approval overlapping an approved booking; cancellation before the start time; concurrent approval tests. | Trang | Phuc |
| 5.4 | Implement history and administration | Resource history, administration and authorized state corrections. Minh also reviews authorization, transactions and data constraints implemented by other members. | Phuc | — |
| 5.4.1 | Record and display history | F08: resource business events and state changes, with actor, outcome, reason when needed and timestamp; Borrowers view their own history, Resource Managers their assigned scope, and Admin all history. Exclude general click/page-view tracking. | Phuc | Trang |
| 5.4.2 | Implement account administration and assignments | F09: create/lock accounts, assign roles and allocate resources to Resource Managers; locking accounts preserves history. | Phuc | Trang |
| 5.4.3 | Implement Admin state corrections | Correct resource and related-request states according to sequence 3.2.9; record before/after values and reasons. | Phuc | Trang |

| 6 Testing and Deployment |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS code | Work item | Expected deliverable | Proposed owner | Proposed reviewer |
| 6.1 | Execute tests and fix defects | Test results, defects, fixes and retesting; Minh supports defect resolution. | Nhat Anh | — |
| 6.1.1 | Prepare the test cycle | Checklist for environment, build/commit, accounts, data and reset procedure; smoke tests for essential flows; confirm entry criteria or record blockers. Reuse seed data from 6.2.3 where appropriate. | Nhat Anh | Minh |
| 6.1.2 | Execute integration tests | API–database and client–API results: access control, approval/reservation/handover/return, room booking and history; pass/fail/blocked status and evidence by test case. | Nhat Anh | Minh |
| 6.1.3 | Execute system tests by role | Manual E2E results for Borrower, Resource Manager and Admin across F01–F09; check UI, API and data state after each flow, including errors and rejection of unauthorized operations. | Nhat Anh | Minh |
| 6.1.4 | Test concurrency and time boundaries | Evidence for concurrent equipment/room approvals, resource release after cancellation, pickup expiry after rescheduling and handover–expiry races; consistency with SRS/ADRs, including before/after data and execution timestamps. | Nhat Anh | Minh |
| 6.1.5 | Build the automated E2E suite | E2E scripts for priority Must-have flows, resettable data and execution instructions; results usable in CI. Minh integrates execution into workflow 6.2.1. | Nhat Anh | Minh |
| 6.1.6 | Execute non-functional tests | Results for cases from 4.2.9: environment, data, measured values, acceptance criteria and limitations; defects or change requests when criteria are not met. | Nhat Anh | Minh |
| 6.1.7 | Record, classify and fix defects | Bug reports with reproduction steps, expected/actual results, severity, build, evidence, fixer and PR links; fixes and status updates by responsible members; code review and passing CI. Nhat Anh coordinates reporting; feature owners fix defects and another member verifies closure. | Nhat Anh | Minh |
| 6.1.8 | Retest fixes and run regression tests | Results for previously failing and affected cases on the corrected build; Nhat Anh or another tester verifies closure or reopens defects and updates the results matrix. | Nhat Anh | Minh |
| 6.1.9 | Summarize results and hand over PA5 evidence | Counts of passed/failed/blocked/not-run cases, requirements coverage and pipeline code coverage; unresolved defects, assessment against exit criteria 4.1.4 and demo limitations; report, log and evidence links sent to Trang for 6.3.1. | Nhat Anh | Minh |
| 6.2 | Deploy the demo | Runtime environment, CI, demo data and deployment instructions. | Minh | — |
| 6.2.1 | Set up CI | GitHub Actions on every PR: formatting, linting, type checking, unit tests with coverage, build and E2E; block merging on failure. | Minh | Nhat Anh |
| 6.2.2 | Deploy the demo environment | Client and API on Vercel, Supabase database, domain through Cloudflare and secrets configured outside the repository; post-deployment smoke tests. | Minh | Nhat Anh |
| 6.2.3 | Create demo data | Seed script with accounts for three roles, equipment, rooms and sample requests in different states. | Minh | Nhat Anh |
| 6.2.4 | Write deployment instructions | Installation, environment variables, local execution, deployment procedure and demo data recovery. | Minh | Nhat Anh |
| 6.3 | Compile the PA5 package and demo video | Implementation/test results package and demo video. | Trang | — |
| 6.3.1 | Compile the PA5 report | Implementation and test results, coverage, demo link, unresolved defects and changes from the PA3/PA4 baselines. | Trang | Phuc |
| 6.3.2 | Record and edit the demo video | Video covering core use cases for all three roles, within the required duration. | Trang | Phuc |
| 6.3.3 | Review and submit PA5 | Rubric checklist, AI log and contribution table; Moodle submission and baseline-pa5 tag. | Trang | Phuc |

| 7 Presentation and Handover |  |  |  |  |
| --- | --- | --- | --- | --- |
| WBS code | Work item | Expected deliverable | Proposed owner | Proposed reviewer |
| 7.1 | Prepare slides and presentation script | Slides and presentation assignments. | Trang | — |
| 7.1.1 | Outline and assign presentation sections | Outline, duration of each section and presenters assigned according to responsibilities. | Trang | Phuc |
| 7.1.2 | Create slides | Slides covering the problem, architecture, demo, testing results, project management and lessons learned. | Trang | Phuc |
| 7.1.3 | Write the live demo script | Demo steps for three roles, sample data and a fallback video for network failure. | Trang | Phuc |
| 7.2 | Rehearse the presentation | Rehearsal results and revised content. | Trang | — |
| 7.2.1 | Run a complete rehearsal | One timed rehearsal with recorded feedback. | Trang | Phuc |
| 7.2.2 | Prepare questions and answers | Anticipated questions for each member's area and agreed answers. | Trang | Phuc |
| 7.2.3 | Revise after rehearsal | Slides and demo script updated in response to feedback. | Trang | Phuc |
| 7.3 | Hand over the product | Source code, user documentation, execution instructions and handover records. | Trang | — |
| 7.3.1 | Package and release | v1.0.0 tag, release notes and updated README. | Trang | Phuc |
| 7.3.2 | Write user documentation | User guides for Borrower, Resource Manager and Admin. | Trang | Phuc |
| 7.3.3 | Submit the final package | Final documentation, confirmation of instructor/TA access to the repository and demo, and handover record. | Trang | Phuc |